## Project Details
(Product)Project Name | CAN 4.0 RoE index based prediction shortlisting Data Source Type addition in Parser
Version | Release 4.0
URL | http://168.63.237.77:8011/CAN/
Reference Documents | https://docs.google.com/document/d/18HfjyjxOJmWKZA1NNp2AVhoCLvbTiwJdKmsJqjbFwCY/edit?ts=5d0cb35b https://docs.google.com/document/d/1DuHKv5IyijSmp2vkV0-QSI2g8T_s_ygEGoxRhN_v1GM/edit#heading=h.36ei31r
Created By | Reshmi Murali (AVT041)
Date of Creation | 24/06/2019
Developer | Rashmi Jyoti, Shlaghana M
Functional Testing:
Start Date: 24/06/2019
End Date: 01/07/2019

## Requirements
Requirement ID (Requirements Document) | Description | Scope | Features Tested(Yes/No) | Test Case Ids
REQ04007 | Allow configuration of weightages to different prediction parameters | Presence of Weightage field as a configuration parameter. | Yes | TCRCA04001 TCRCA04002
REQ04008 | Default factory settings should be provided for RoE parameters and corresponding weights. | Presence of Default values in the Configurations fields as soon as we enter into the page. | Yes | TCRCA04003 TCRCA04004 TCRCA04005
REQ04009 | By default, it should be enabled. | Status tab should be set as Enabled for the very first time. | Yes | TCRCA04006 TCRCA04007
REQ04010 | Allow selection of excel report sheets on which RoE has to be applied | Configured Excel sheets list to be present in the drop down. | Yes | TCRCA04008 TCRCA04009 TCRCA04010
REQ04011 | Allow configuration of selecting desired prediction records by writing multiple queries. | Option to Add multiple queries. | Yes | TCRCA04011
REQ04012 | Allow configuration of linking existing excel sheet to another sheets to which RoE configuration has been applied | Linking of configured excel sheets | Yes | TCRCA04012
REQ04013 | Allow configuration of how many prediction groups have to be prioritized. | Validating the value that can be entered in No. of Primary Predictions | Yes | TCRCA04013
REQ04014 | Allow configuration of primary color showing that the record is being prioritized based on RoE | Vaidating the selected Primary and Secondary colors. | Yes | TCRCA04014
REQ04015 | Generate report based on RoE | Report Generation. | Yes | TCRCA04015
REQ04016 | Merging or sorting of rows should be disabled if RoE is active and vice versa. This is needed since both are trying to rearrange predicted faults and only one should be allowed. | Validating the functionality of Status bootstrap with Merge and Sort of Report Configuration. | Yes | TCRCA04016
DATA SOURCE TYPE ADDITION IN PARSER
REQ04035 | Allow selection option for data source in parser screen | All the data source options should be displayed in the parser screen. | Yes | TCDST04001 TCDST04002 TCDST04003
REQ04036 | Mandatory fields in case of different data source types have to be configured | All Mandatory fields should be mapped to the file that has to be parsed with respect to the respective data sources. | Yes | TCDST04004 TCDST04005
REQ04037 | Data collection followed by parsing should store the data in the selected data source tables in the DB. | All the data that has been parsed should be available in the respective data source collections in the DB. | Yes | TCDST04006
REQ04038 | Audit logs should be generated for files processed of each type | Verify the Audit logs in parser Audit table and verify if the count of aggregated records is as expected | Yes | TCDST04007

## ROE_Functional
Requirement ID | Requirement Description | Test Case ID | Test Case Heading | Pre-Requisites | Steps to Test | Actual Result | Expected Result | Pass/Fail | Defect ID | Consider for Regression Testing(Yes/No) | Comments
REQ04007 | Allow configuration of weightages to different prediction parameters | TCROE04001 | Verify the RoE Configuration page. | Test Environment availability. Database access. To be tested in IE, FF and GC. | Step 1: Login to CAN Application. Step 2: Click on Adaptation in the Developer section. Step 3: Click on RoE Configuration. Step 4: Verify if Weightage Configuration and Sheet Configuration tabs are present and Weightage Configuration is selected by default. | Login should be successful and Executive Dashboard screen should be displayed. Adaptation screen should be displayed. User is navigated to the RoE Configuration page. Weightage Configuration and Sheet Configuration tabs are present and Weightage Configuration is selected by default. | Login should be successful and Executive Dashboard screen should be displayed. Adaptation screen should be displayed. User is navigated to the RoE Configuration page. Weightage Configuration and Sheet Configuration tabs are present and Weightage Configuration is selected by default. | Pass
|  | TCROE04002 | Verify the functionality of Weightage RoE Configuration parameters under Weightage Configuration. | Test Environment availability. Database access. To be tested in IE, FF and GC. | Step 1: Login to CAN Application. Step 2: Click on Adaptation in the Developer section. Step 3: Click on RoE Configuration. Step 4: Verify if Weightage Configuration and Sheet Configuration tabs are present and Weightage Configuration is selected by default. Step 5: Verify if the parameter "Weightage " is present. Step 6: If only 1 entry is present and if the value is < 1 in the Weightage field, click on update button and verify if the following message is displayed: "Sum of the weightages should be equal to 1" . | Login should be successful and Executive Dashboard screen should be displayed. Adaptation screen should be displayed. User is navigated to the RoE Configuration page. Weightage Configuration and Sheet Configuration tabs are present and Weightage Configuration is selected by default. "Weightage" parameter is present. If only 1 entry is present and if the value is < 1 in the Weightage field, after clicking on update button,the following message is displayed: "Sum of the weightages should be equal to 1". | Login should be successful and Executive Dashboard screen should be displayed. Adaptation screen should be displayed. User is navigated to the RoE Configuration page. Weightage Configuration and Sheet Configuration tabs are present and Weightage Configuration is selected by default. "Weightage" parameter is present. If only 1 entry is present and if the value is < 1 in the Weightage field, after clicking on update button,the following message is displayed: "Sum of the weightages should be equal to 1". | Pass
REQ04008 | Default factory settings should be provided for RoE parameters and corresponding weights. | TCROE04003 | Verify RoE Configuration parameters under Weightage tab. | Test Environment availability. Database access. To be tested in IE, FF and GC. | Step 1: Login to CAN Application. Step 2: Click on Adaptation in the Developer section. Step 3: Click on RoE Configuration. Step 4: Verify if Weightage Configuration and Sheet Configuration tabs are present and Weightage Configuration is selected by default. Step 5: Verify if the following fields are available under Weightage section: Parameter with dropdown values to be selected. Parameter value should have edit buttons for each parameter selected. Lower limit Upper limit Limit logic with edit buttons Weightage, mandatory field Delete button Step 6: Verify if the below notes are present below these configurations: * : Mandatory Field ** : For each parameter, fill up upper limit and lower limit or write a logic to set limits. Step 7: An Add new button and an Update button should also be present. | Login should be successful and Executive Dashboard screen should be displayed. Adaptation screen should be displayed. User is navigated to the RoE Configuration page. Weightage Configuration and Sheet Configuration tabs are present and Weightage Configuration is selected by default. The above mentioned parameters are present. The notes mentioned are present below the configuration parameters. Add new button and Update button are also present. | Login should be successful and Executive Dashboard screen should be displayed. Adaptation screen should be displayed. User is navigated to the RoE Configuration page. Weightage Configuration and Sheet Configuration tabs are present and Weightage Configuration is selected by default. The above mentioned parameters are present. The notes mentioned are present below the configuration parameters. Add new button and Update button are also present. | Pass
|  | TCROE04004 | Values of each parameters | Test Environment availability. Database access. To be tested in IE, FF and GC. | Step 1: Parameter field should have a dropdown with 7 values. Step 2: Edit button with and without a blue dot. Step 3: Lower limit and Upper limit should be able to accept only numbers. Step 4: Limit Logic as an edit button for setting the upper and lower limits. Step 5: Weightage should accept any numbers from 0.0 to 1.0 Step 6: Delete button should be present to delete a particular row of the RoE configuration. | Parameter field is a dropdown with 7 values that can be selected. Once one value is selected, then that particular value will be disabled. Edit button with a blue dot indicates that a code has already been written for that parameter value. For few values, only edit button will be present. If we click on that, we will be able to write the code, compile it and save it. Lower limit and Upper limit accepts only numbers. A logic is written to set limits incase, upper limit and lower limit is not set manually. Weightage accepts any numbers from 0.0 to 1.0 Delete button is present to delete the particular row of RoE configuration. | Parameter field is a dropdown with 7 values that can be selected. Once one value is selected, then that particular value will be disabled. Edit button with a blue dot indicates that a code has already been written for that parameter value. For few values, only edit button will be present. If we click on that, we will be able to write the code, compile it and save it. Lower limit and Upper limit accepts only numbers. A logic is written to set limits incase, upper limit and lower limit is not set manually. Weightage accepts any numbers from 0.0 to 1.0 Delete button is present to delete the particular row of RoE configuration. | Pass | DFCT_04_011 DFCT_04_012 Defects are fixed and closed.
|  | TCROE04005 | Verify if Default Factory Settings are present. | Test Environment availability. Database access. To be tested in IE, FF and GC. | Step 1: Login to CAN Application. Step 2: Click on Adaptation in the Developer section. Step 3: Click on RoE Configuration. Step 4: Verify if Weightage Configuration and Sheet Configuration tabs are present and Weightage Configuration is selected by default. Step 5: Verify if Default Factory Settings are present as soon as we navigate to the RoE Configuration page. | Login should be successful and Executive Dashboard screen should be displayed. Adaptation screen should be displayed. User is navigated to the RoE Configuration page. Weightage Configuration and Sheet Configuration tabs are present and Weightage Configuration is selected by default. Default Factory Settings are present as soon as we navigate to the RoE Configuration page. | Login should be successful and Executive Dashboard screen should be displayed. Adaptation screen should be displayed. User is navigated to the RoE Configuration page. Weightage Configuration and Sheet Configuration tabs are present and Weightage Configuration is selected by default. Default Factory Settings are present as soon as we navigate to the RoE Configuration page. | Pass | DFCT_04_011 Defect Fixed and Closed
REQ04009 | By default, it should be enabled. | TCROE04006 | Verify if the Status field is enabled by default. | Test Environment availability. Database access. To be tested in IE, FF and GC. | Step 1: Login to CAN Application. Step 2: Click on Adaptation in the Developer section. Step 3: Click on RoE Configuration. Step 4: Verify if the Status is enabled by default. | Login should be successful and Executive Dashboard screen should be displayed. Adaptation screen should be displayed. User is navigated to the RoE Configuration page. Weightage Configuration and Sheet Configuration tabs are present and Weightage Configuration is selected by default. Status should be enabled by default. Note: If the Status is changed to Disabled, then the next time we login , it will be in Disabled state only. | Login should be successful and Executive Dashboard screen should be displayed. Adaptation screen should be displayed. User is navigated to the RoE Configuration page. Weightage Configuration and Sheet Configuration tabs are present and Weightage Configuration is selected by default. Status should be enabled by default. Note: If the Status is changed to Disabled, then the next time we login , it will be in Disabled state only. | Pass
|  | TCROE04007 | Verify if Merge and Sort options in Report Configuration are disabled if RoE is active. | Test Environment availability. Database access. To be tested in IE, FF and GC. | Step 1: Login to CAN Application. Step 2: Click on Adaptation in the Developer section. Step 3: Click on RoE Configuration. Step 4: Verify if the Status is enabled by default. Step 5: Click on Back to Settings button and click on Report Configuration. Step 6: Under Page Configuration, verify if Merge and Sort options are disabled and following Note is present: "MERGE and SORT options are disabled as RoE is active" | Login should be successful and Executive Dashboard screen should be displayed. Adaptation screen should be displayed. User is navigated to the RoE Configuration page. Weightage Configuration and Sheet Configuration tabs are present and Weightage Configuration is selected by default. Status should be enabled by default. Report Configuration page should be displayed and Page Configuration should be selected by default. "MERGE and SORT options are disabled as RoE is active" message is present under Page Configuration. Note: When the status/RoE Configuration is disabled, the Merge and Sort options in Report Configuration will get enabled. | Login should be successful and Executive Dashboard screen should be displayed. Adaptation screen should be displayed. User is navigated to the RoE Configuration page. Weightage Configuration and Sheet Configuration tabs are present and Weightage Configuration is selected by default. Status should be enabled by default. Report Configuration page should be displayed and Page Configuration should be selected by default. "MERGE and SORT options are disabled as RoE is active" message is present under Page Configuration. Note: When the status/RoE Configuration is disabled, the Merge and Sort options in Report Configuration will get enabled. | Pass
REQ04010 | Allow selection of excel report sheets on which RoE has to be applied | TCROE04008 | Verify Sheet configuration tab under RoE Configuration. | Test Environment availability. To be tested in IE, FF and GC. Database Access. | Step 1: Login to CAN Application. Step 2: Click on Adaptation in the Developer section. Step 3: Click on RoE Configuration. Step 4: Click on Sheet Configuration. Step 5: Verify if any sheets are present under the Sheet Configuration page for the very 1st time. Step 6: Verify RoeConfig table is present in the database. | Login should be successful and Executive Dashboard screen should be displayed. Adaptation screen should be displayed. User is navigated to the RoE Configuration page. Sheet Configuration should have the following message highlighted : "No sheets are configured. Please add new sheet !" For the very 1st time, if no sheets are added or if no sheets are present, then RoeConfig table will not be rpesent in the Database. | Login should be successful and Executive Dashboard screen should be displayed. Adaptation screen should be displayed. User is navigated to the RoE Configuration page. Sheet Configuration should have the following message highlighted : "No sheets are configured. Please add new sheet !" For the very 1st time, if no sheets are added or if no sheets are present, then RoeConfig table will not be rpesent in the Database. | Pass
|  | TCROE04009 | Add new sheet under Sheet Configuration. | Test Environment availability. To be tested in IE, FF and GC. Database Access. | Step 1: Login to CAN Application. Step 2: Click on Adaptation in the Developer section. Step 3: Click on RoE Configuration. Step 4: Click on Sheet Configuration. Step 5: Click on Add new sheet dropdown. Step 6: Click on the sheets one by one. Step 7: Verify RoeConfig table is present in the database. | Login should be successful and Executive Dashboard screen should be displayed. Adaptation screen should be displayed. User is navigated to the RoE Configuration page. Sheet Configuration should have the following message highlighted : "No sheets are configured. Please add new sheet !" The dropdown should have all the configured excel sheets. The selected sheets should be added to the sheet configuration. RoeConfig table should have the details of the sheets added in the Sheet configuration.(No.of sheets = No.of records in Db ) | Login should be successful and Executive Dashboard screen should be displayed. Adaptation screen should be displayed. User is navigated to the RoE Configuration page. Sheet Configuration should have the following message highlighted : "No sheets are configured. Please add new sheet !" The dropdown should have all the configured excel sheets. The selected sheets should be added to the sheet configuration. RoeConfig table should have the details of the sheets added in the Sheet configuration.(No.of sheets = No.of records in Db ) | Pass
|  | TCROE04010 | Configure sheets from Report Configuration. | Test Environment availability. To be tested in IE, FF and GC. Database Access. | Step 1: Login to CAN Application. Step 2: Click on Adaptation in the Developer section. Step 3: Go to Report Configuration-> Excel Report->Click on Add New sheet button. Step 4: Add new sheet details and click on update. Step 5: Go to RoEConfiguration->Sheet Configuration Step 6: Verify if the Add New Sheet dropdown has all the excel sheets configured from Report configuration. Step 7: Click on the sheets one by one. Step 8: Verify the records generated in the RoeConfig database. | Login should be successful and Executive Dashboard screen should be displayed. Adaptation screen should be displayed. A new row should be added for the new sheet configuration. The new sheet details should be updated successfully. Sheet Configuration page should be displayed. In the Add new sheet dropdown all the sheets that was added in Report Configuration should be displayed. The sheets selected should be added to Sheet Configuration. The new sheets details should be present as new records in the RoeConfig table. | Login should be successful and Executive Dashboard screen should be displayed. Adaptation screen should be displayed. A new row should be added for the new sheet configuration. The new sheet details should be updated successfully. Sheet Configuration page should be displayed. In the Add new sheet dropdown all the sheets that was added in Report Configuration should be displayed. The sheets selected should be added to Sheet Configuration. The new sheets details should be present as new records in the RoeConfig table. | Pass
REQ04011 | Allow configuration of selecting desired prediction records by writing multiple queries. | TCROE04011 | Verify if configuration can be done for specfic predictions with multiple queries | Test Environment availability. To be tested in IE, FF and GC. Database Access. | Step 1: Login to CAN Application. Step 2: Click on Adaptation in the Developer section. Step 3: Go to RoEConfiguration->Sheet Configuration Step 4: Verify if the Add New Query button is present. Step 7: Click on the Add New Query button. Step 8: Verify if a textbox with close(X) button and 3 dots are present. Step 9: Click on the Text box. Step 10: Enter a query in Json format and click on update button. Step 11: Repeat Step 7, 9 and 10 for writing multiple queries. Step 12: Verify if the modifications are reflected in the roeConfig table in the database. | Login should be successful and user should be navigated to the Executive Dahsboard screen. Navigates to the Adaptation screen. Sheet Configuration screen is displayed. Add New Query button is present. A new text box is added. A close button and 3 dots where we have options to fix the position of the queries. A window is opened for writing the query. Query should be wriiten in the Json format and it should get updated successfully. We should be able to write multiple queries. The details of the added queries should be reflected in the RoeConfig table of the database. | Login should be successful and user should be navigated to the Executive Dahsboard screen. Navigates to the Adaptation screen. Sheet Configuration screen is displayed. Add New Query button is present. A new text box is added. A close button and 3 dots where we have options to fix the position of the queries. A window is opened for writing the query. Query should be wriiten in the Json format and it should get updated successfully. We should be able to write multiple queries. The details of the added queries should be reflected in the RoeConfig table of the database. | Pass
REQ04012 | Allow configuration of linking existing excel sheet to another sheets to which RoE configuration has been applied | TCROE04012 | Verify if existing excel sheets can be linked to other excel sheets. | Test Environment availability. To be tested in IE, FF and GC. Database Access. | Step 1: Login to CAN Application. Step 2: Click on Adaptation in the Developer section. Step 3: Go to Report Configuration-> Excel Report->Click on Add New sheet button. Step 4: Add new sheet details and click on update. Step 5: Go to RoEConfiguration->Sheet Configuration Step 6: Verify if the Add New Sheet dropdown has all the excel sheets configured from Report configuration. Step 7: Click on the linking button on the added sheet and link the sheets. Step 8: Verify the records generated in the RoeConfig database. | Login should be successful and Executive Dashboard screen should be displayed. Adaptation screen should be displayed. A new row should be added for the new sheet configuration. The new sheet details should be updated successfully. Sheet Configuration page should be displayed. In the Add new sheet dropdown all the sheets that was added in Report Configuration should be displayed. A new window is opened where all the sheets that can be linked to this sheet are present. Note: Any number of sheets can be configured if they do not have an individual configuration. The linked sheets details should be present as new records in the RoeConfig table. | Login should be successful and Executive Dashboard screen should be displayed. Adaptation screen should be displayed. A new row should be added for the new sheet configuration. The new sheet details should be updated successfully. Sheet Configuration page should be displayed. In the Add new sheet dropdown all the sheets that was added in Report Configuration should be displayed. A new window is opened where all the sheets that can be linked to this sheet are present. Note: Any number of sheets can be configured if they do not have an individual configuration. The linked sheets details should be present as new records in the RoeConfig table. | Pass
REQ04013 | Allow configuration of how many prediction groups have to be prioritized. | TCROE04013 | Verify the functionality of No. of Primary predictions | Test Environment availability. To be tested in IE, FF and GC. Database Access. | Step 1: Login to CAN Application. Step 2: Click on Adaptation in the Developer section. Step 3: Go to RoE Configuration->Sheet Configuration. Step 4: Verify if the field No. of Primary predictions is present. Step 5: Verify if an integer upto 50000 only can be added into No. of Primary Predictions field. | Login should be successful and user should be navigated to the Executive Dashboard screen. Navigates to the Adaptation screen. Sheet Configuration page is displayed. No. of Primary Predictions field is present with a textbox where values can be inserted. No. of Predictions field accepts only an integer and the maximum value that it accepts it 50000. | Login should be successful and user should be navigated to the Executive Dashboard screen. Navigates to the Adaptation screen. Sheet Configuration page is displayed. No. of Primary Predictions field is present with a textbox where values can be inserted. No. of Predictions field accepts only an integer and the maximum value that it accepts it 50000. | Pass | DFCT_04_013 Defect fixed and closed.
REQ04014 | Allow configuration of primary color showing that the record is being prioritized based on RoE | TCROE04014 | Verify the functionality of primary color configuration | Test Environment availability. To be tested in IE, FF and GC. Database Access. | Step 1: Login to CAN Application. Step 2: Click on Adaptation in the Developer section. Step 3: Go to RoE Configuration->Sheet Configuration. Step 4: Verify if the field Color code is present. | Login should be successful and user should be navigated to the Executive Dashboard screen. Navigates to the Adaptation screen. Sheet Configuration page is displayed. Color Code field is present with a textbox and a color that is already selected to highlight primary predictions with the secondary color. Note: When we click on the color, a colorpicker is displayed, where we can select the Primary color.The secondary color is automatically taken with respect to the primary color choosen. These colors will be highlighted in the report we generate. | Login should be successful and user should be navigated to the Executive Dashboard screen. Navigates to the Adaptation screen. Sheet Configuration page is displayed. Color Code field is present with a textbox and a color that is already selected to highlight primary predictions with the secondary color. Note: When we click on the color, a colorpicker is displayed, where we can select the Primary color.The secondary color is automatically taken with respect to the primary color choosen. These colors will be highlighted in the report we generate. | Pass
REQ04015 | Generate report based on RoE | TCROE04015 | Generation of Reports based on RoE configuration | Test Environment availability. To be tested in IE, FF and GC. Database Access. | Step 1: Login to the CAN Application. Step 2: Complete all the required RoE Configurations under Weightage Configuration and Sheet Configuration. Step 3: Run the testRoe.jsp <HostIP>/CAN/testRoe.jsp and click on enter. Step 4: Go to Database and verify if weightIndex field has beed generated in the Predicted Fault Table. Step 5: Run the reportEmail.jsp Step 6: Open the Excel and verify if the sheets in the excel are as per the RoE Configuration. | Login should be successful and the user should be navigated to the Executive Dashboard screen. All the RoE Configurations should be done as required. Enter the username and password and this should generate the weightIndex in the DB. weightIndex field has beed generated in the Predicted Fault Table. The RoE configured excel sheet will be sent to the configured mail id. The excel sheet is configured and the values in the excel sheet are as per the RoE Configuration. | Login should be successful and the user should be navigated to the Executive Dashboard screen. All the RoE Configurations should be done as required. Enter the username and password and this should generate the weightIndex in the DB. weightIndex field has beed generated in the Predicted Fault Table. The RoE configured excel sheet will be sent to the configured mail id. The excel sheet is configured and the values in the excel sheet are as per the RoE Configuration. | Pass
REQ04016 | Merging or sorting of rows should be disabled if RoE is active and vice versa. This is needed since both are trying to rearrange predicted faults and only one should be allowed. | TCROE04016 | Refer TCRCA04007 |  |  |  |  | Pass

## DataSourceType_Functional
Requirement ID | Requirement Description | Test Case ID | Test Case Heading | Pre-Requisites | Steps to Test | Actual Result | Expected Result | Pass/Fail | Defect ID | Consider for Regression Testing(Yes/No) | Comments
REQ04035 | Allow selection option for data source in parser screen | TCDST04001 | Verify if all the Data Source Type are listed in the Parser Screen. | Test Environment availability. To be tested in IE, FF and GC browsers. | Step 1: Login to CAN Application. Step2: Go to Developer Section and click on Adaptation. Step 3: Click on Parser. Step 4: Verify if the below Data source type buttons are present under the Data Source section: Alarm Ticket Performance Counter Others | Login should be successful and user should get navigated to the Executive Dashboard screen. Adaptation screen is displayed. Input Mapper Screen is displayed. The above mentioned fields are data source type buttons are present under the Data Source section. | Login should be successful and user should get navigated to the Executive Dashboard screen. Adaptation screen is displayed. Input Mapper Screen is displayed. The above mentioned fields are data source type buttons are present under the Data Source section. | Pass
|  | TCDST04002 | Verify if the configured parsers are present for each of the Data Source Types under the Saved Mappings section. | Test Environment availability. To be tested in IE, FF and GC browsers. | Step 1: Login to CAN Application. Step2: Go to Developer Section and click on Adaptation. Step 3: Click on Parser. Step 4: Verify if the below Data source type buttons are present under the Data Source section: Alarm Ticket Performance Counter Others Step 5: Verify if the configured parsers are present for each of the Data Source Types under the Saved Mappings section. | Login should be successful and user should get navigated to the Executive Dashboard screen. Adaptation screen is displayed. Input Mapper Screen is displayed. The above mentioned fields are data source type buttons are present under the Data Source section. The configured parsers are present for each of the Data Source Types under the Saved Mappings section. | Login should be successful and user should get navigated to the Executive Dashboard screen. Adaptation screen is displayed. Input Mapper Screen is displayed. The above mentioned fields are data source type buttons are present under the Data Source section. The configured parsers are present for each of the Data Source Types under the Saved Mappings section. | Pass
|  | TCDST04003 | Verify the fields under File Level Info section for each of the Data Source Type | Test Environment availability. To be tested in IE, FF and GC browsers. | Step 1: Login to CAN Application. Step2: Go to Developer Section and click on Adaptation. Step 3: Click on Parser. Step 4: Verify if the below Data source type buttons are present under the Data Source section: Alarm Ticket Performance Counter Others Step 5: Verify if the following fields are present under the File Level Info section for each of the Data Source Types: Name, mandatory field Description, mandatory filed File Type Page Size, mandatory field Pre-processor Post-processor A bootstrpa which has values Yes/No for Header SheetName with "?", while hovering displayes a message. | Login should be successful and user should get navigated to the Executive Dashboard screen. Adaptation screen is displayed. Input Mapper Screen is displayed. The above mentioned fields are data source type buttons are present under the Data Source section. The above mentioned fields are present under the File Level Info section for each of the Data Source Types. | Login should be successful and user should get navigated to the Executive Dashboard screen. Adaptation screen is displayed. Input Mapper Screen is displayed. The above mentioned fields are data source type buttons are present under the Data Source section. The above mentioned fields are present under the File Level Info section for each of the Data Source Types. | Pass
REQ04036 | Mandatory fields in case of different data source types have to be configured | TCDST04004 | Verify if all the mandatory fields for each of the datasource types have been configured. | Test Environment availability. To be tested in IE, FF and GC browsers. | Step 1: Login to CAN Application. Step2: Go to Developer Section and click on Adaptation. Step 3: Click on Parser. Step 4: Verify if the below Data source type buttons are present under the Data Source section: Alarm Ticket Performance Counter Others Step 5: Click on any one of the Datasource Types and verify if the mandatory fields are mapped to the file that has to be parsed. Step 6: Repeat Step6 for all the other Data Source Types. | Login should be successful and user should get navigated to the Executive Dashboard screen. Adaptation screen is displayed. Input Mapper Screen is displayed. The above mentioned fields are data source type buttons are present under the Data Source section. All the mandatory fields are supposed to be mapped. Note: The mandatory fields will not have the Delete button present. All the mandatory fields are supposed to be mapped for all the other data source types as well. | Login should be successful and user should get navigated to the Executive Dashboard screen. Adaptation screen is displayed. Input Mapper Screen is displayed. The above mentioned fields are data source type buttons are present under the Data Source section. All the mandatory fields are supposed to be mapped. Note: The mandatory fields will not have the Delete button present. All the mandatory fields are supposed to be mapped for all the other data source types as well. | Pass
|  | TCDST04005 | Verify all the CAN fields of the Data Source Types | Test Environment availability. To be tested in IE, FF and GC browsers. | Step 1: Login to CAN Application. Step2: Go to Developer Section and click on Adaptation. Step 3: Click on Parser. Step 4: Verify if the below Data source type buttons are present under the Data Source section: Alarm Ticket Performance Counter Others Step 5: Click on any one of the Datasource Types and click on the "+" symbol beside the field "CAN field" and verify if all the required fields for mapping the respective data sources are available. | Login should be successful and user should get navigated to the Executive Dashboard screen. Adaptation screen is displayed. Input Mapper Screen is displayed. The above mentioned fields are data source type buttons are present under the Data Source section. Clicking on the "+" symbol opens another window and displays all the CAN fields required for mapping for the respective Data Source types. Note: We can click on the particular field and get it added on the parser screen for mapping. Once one field is added, that field will get deleted from this list. | Login should be successful and user should get navigated to the Executive Dashboard screen. Adaptation screen is displayed. Input Mapper Screen is displayed. The above mentioned fields are data source type buttons are present under the Data Source section. Clicking on the "+" symbol opens another window and displays all the CAN fields required for mapping for the respective Data Source types. Note: We can click on the particular field and get it added on the parser screen for mapping. Once one field is added, that field will get deleted from this list. | Pass
REQ04037 | Data collection followed by parsing should store the data in the selected data source tables in the DB. | TCDST04006 | Verify if the data is stored in the respective Collections after parsing is completed. | Test Environment availability. To be tested in IE, FF and GC browsers. Database access. | Step 1: Login to CAN Application. Step2: Go to Developer Section and click on Adaptation. Step 3: Click on Parser. Step 4: With respect to the file that has to be parsed, configure the parser for the respective Data Source. Step 5: Click on Back to Settings button and click on File Collection. Step 6: Complete the configuration for the file in the File Collection page. Step 7: Run pickupData.jsp http://<hostIP:portnumber>/CAN/pickupData.jsp Step 8: Verify the respective Data Source tables in the DB and verify if the value of the "completed" field is true. Step 9: After completion of parsing, take the parserAuditId from the ParserAudit table and verify the same with the parserAuditID in the respective DataSource table. Step 10: Verify if the total records in the ParserAudit table matches the number of records in the parsed file. | Login should be successful and user should navigated to the Executive Dashboard screen. Adaptation page should be displayed. Input Mapper Screen is displayed. The parser for the respective data source should be configured for the file. File Collection screen is displayed. All the configurations is completed in the File Collection page. pickupData.jsp is run successfully. In the parserAudit table, the value for "completed" field is true once the parsing is completed. The total records in the ParserAudit table matches the number of records in the parsed file. The logs of the parsed file should be displayed in the Data Collection Audit tab of the Monitoring screen. | Login should be successful and user should navigated to the Executive Dashboard screen. Adaptation page should be displayed. Input Mapper Screen is displayed. The parser for the respective data source should be configured for the file. File Collection screen is displayed. All the configurations is completed in the File Collection page. pickupData.jsp is run successfully. In the parserAudit table, the value for "completed" field is true once the parsing is completed. The total records in the ParserAudit table matches the number of records in the parsed file. The logs of the parsed file should be displayed in the Data Collection Audit tab of the Monitoring screen. | Pass
REQ04038 | Audit logs should be generated for files processed of each type | TCDST04007 | Verify the Audit logs to be generated for each of the data source types. | Test Environment availability. To be tested in IE, FF and GC browsers. Database access. | Step 1: Login to CAN Application. Step2: Go to Developer Section and click on Adaptation. Step 3: Click on Parser. Step 4: With respect to the file that has to be parsed, configure the parser for the respective Data Source. Step 5: Click on Back to Settings button and click on File Collection. Step 6: Complete the configuration for the file in the File Collection page. Step 7: Run pickupData.jsp http://<hostIP:portnumber>/CAN/pickupData.jsp Step 8: Verify the respective parserAudit tables in the DB and verify if the value of the "completed" field is true. Step 9: After completion of parsing, take the parserAuditId from the ParserAudit table and verify the same with the parserAuditID in the respective DataSource table. Step 10: Verify if the total records in the ParserAudit table matches the number of records in the parsed file. Step 11: In the UI, go to Monitoring section and verify the logs of the parsed file in the Data Collection Audit tab. Step 12: In the RootCauseAnalysis table, verify the count of the ParserAuditID: eg:db.Alarm.count({parserAuditId:"5d19df7ebb19a802305df941"}) | Login should be successful and user should navigated to the Executive Dashboard screen. Adaptation page should be displayed. Input Mapper Screen is displayed. The parser for the respective data source should be configured for the file. File Collection screen is displayed. All the configurations is completed in the File Collection page. pickupData.jsp is run successfully. In the parserAudit table, the value for "completed" field is true once the parsing is completed. The total records in the ParserAudit table matches the number of records in the parsed file. The logs of the parsed file should be displayed in the Data Collection Audit tab of the Monitoring screen. In the RootCauseAnalysis table, the count of the ParserAuditID should match the count of the aggregated records in ParserAudit table. | Login should be successful and user should navigated to the Executive Dashboard screen. Adaptation page should be displayed. Input Mapper Screen is displayed. The parser for the respective data source should be configured for the file. File Collection screen is displayed. All the configurations is completed in the File Collection page. pickupData.jsp is run successfully. In the parserAudit table, the value for "completed" field is true once the parsing is completed. The total records in the ParserAudit table matches the number of records in the parsed file. The logs of the parsed file should be displayed in the Data Collection Audit tab of the Monitoring screen. In the RootCauseAnalysis table, the count of the ParserAuditID should match the count of the aggregated records in ParserAudit table. | Pass

## Defects
Defect ID | Defect HeadLine | Test Level (Functional/Regression) | Prerequisites and Steps to Follow | Requirement ID | Test Case Id | Priority/ Severity | Assigned To | Defect Status | Comments | Screenshots for reference
DFCT_04_011 | After clearing, the code is not getting compiled again when the same class name is given. | ROE_Functional | 1. Login to CAN 4.0 2. Click on RoE tab. 3. Click on Add new button. 4. Select a new parameter from the dropdown. 5. Click on edit button. 6. Give a classname, enter the code, click on compile. 7. Click on Clear button. 8. Repeat Step 6 with the same classname. Actual Result: No code is getting generated once Compile button is clicked. Expected Result: The compiled code should get generated. | REQ04008 | TCRCA04004 | High | Rashmi Jyoti | New-> Open->Fixed->Retested->Closed |  | Screenshot1
DFCT_04_012 | If the same class is not accepted, no message is shown to the user. | ROE_Functional | 1. Login to CAN 4.0 2. Go to Adaptation->Click on RoE Configuration tab. 3. Click on Add new button. 4. Select a new parameter from the dropdown. 5. Click on edit button. 6. Give a classname, enter the code, click on compile and save. 7. Repeat Step 3 and Step 4. 8. Give the same class name as of Step 6 and click on compile. Actual Result: No message is displayed due usage of same classnames. Expected Result: As we are using the same name, code does not get compiled and this should be notified to the users. | REQ04008 | TCRCA04004 | Medium | Rashmi Jyoti | New-> Open->Fixed->Retested->Closed
DFCT_04_013 | No. of Primary predictions is taking decimal values as input. | ROE_Functional | 1. Login to CAN 4.0 2. Go to Adaptation->Click on RoE Configuration tab. 3. Click on Sheet Configuration tab. 4. Enter Decimal values in No. of Primary prediction textbox. Actual Result: No. of Primary predictions is taking decimal values as input. Expected Result: No. of Primary predictions should not take decimal values as input. | REQ04011 | TCRCA04013 | High | Rashmi Jyoti | New-> Open->Fixed->Retested-> Closed |  | Screenshot2

## Screenshots
Screenshot1
Screenshot2

## Report
STATUS REPORT
No of requirements | 14
Total no. of Test cases | 23
No .of Test cases passed | 23
No.of Test cases failed | 0
Defect Status
Total Defects Raised | 3 | 2- High 1-Medium
No. of Open Defects | 0
Defect Status